## Dept Obj
DEPT OBJS
Finances | Full Year | HR | Management | Marketing | Operations | Pedagogy | Resources - Israel | Resources - USA | Tech
Choose Internal Audit Committee | Recruit fellows | Recruitment |  |  |  | Improve communication and collaboration | Optimizing development team operations | Coordinate alumni events | Evaluation and Measurement
Completion of Volunteers Report | Find Housing for Fellows | HR Measurement & Evaluation |  |  |  | Evaluate and Measure TALMA programs | Develop funding sources | Cooperation between Resource Departments | Improve Internal Tools
Initiation of Additional Report – Corporate Governance | Routine Follow-up | Onboarding |  |  |  | Hire and retain high-quality teachers effectively | Strengthen existing funders | Improve Professional Skills | Improve Data Security | Optimizing development team operations | Optimizing development team operations
Review of Payroll Preparation Process | PD | Culture & Welfare |  |  |  | Strengthen Professional Development | Develop income generating initiatives | Recruit teachers | Map existing hardware providers | לתת פה שם | Optimizing development team operations
Transition to Attendance Reporting in MYHR System | Fellow Development | Compliance |  |  |  | Deepen Professional Expertise | Increasing potential financial partners exposure to TALMA | Represent TALMA at Events | Map existing software systems |  | Optimizing development team operations
Automatic Pension Enrollment | Observation & Evaluation | Offboarding |  |  |  | Create and Deliver Pedagogical Content | Develop new municipalties | Send Newsletters | Improve Client Facing Tools | לתת שם - חיבור וסנכרון למאנדיי | לתת פה שם
Develop Internal Financial Information System | Returners | Office Operations |  |  |  |  | Strengthen existing municipalties | Conduct Team Evaluations Feedback |  | Diversify funding sources
Transition to Monthly Budget and Cash Flow Monitoring | Orientation & Onboarding | Retention | [5 empty] | Manage Fellowship administration |  | Diversify funding sources / להפריד לגראנטים | לתת שם - חיבור וסנכרון למאנדיי
Build a Profit Center and Cost Allocation Model | School Collaboration Setup | Conference Management | [5 empty] | Present TALMA to educators |  | קשר עם תורמים(?) | לתת שם - חיבור וסנכרון למאנדיי
Measure Profitability of Organizational Programs | End-Year Review | Improve Employee Retention | [5 empty] | Raise funds |  | Develop income generating initiatives
Manage the Organization's Annual Budget | Place Fellows in Regions | [6 empty] | Manage Alumni Network |  | Increasing potential financial partners exposure to TALMA | Diversify funding sources
| Lead TALMA Tuesday Sessions | [9 empty] | Diversify funding sources / להפריד לגראנטים
| Manage Routine Program Operations | [9 empty] | Diversify funding sources
| Support Fellows | [9 empty] | Diversify funding sources
Diversify funding sources
Diversify funding sources
Diversify funding sources
Diversify funding sources
Diversify funding sources
קשר עם תורמים(?)
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Increasing potential financial partners exposure to TALMA
Increasing potential financial partners exposure to TALMA
Diversify funding sources
Diversify funding sources
Diversify funding sources
Diversify funding sources
Diversify funding sources
קשר עם תורמים(?)
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Develop income generating initiatives
Increasing potential financial partners exposure to TALMA
Increasing potential financial partners exposure to TALMA
תוכנית שנתית- גאנט עבודה
תוכנית הקיץ- גאנט עבודה
פרויקטים שנתיים- גאנט עבודה (מרחבים, נס ציונה, בני עייש)

## Focus Areas
FOCUS AREAS
ALL | Finances | Full Year | HR | Management | Marketing | Operations | Pedagogy | Resources - Israel | Resources - USA | Tech
Additional Report | Grants | FY management | MyHR | Interdepartment Communication | Website Advertising |  | Full Year | TALMA Events - Ministry of Science | Alumni | Bnei Ayish
Aharai | MyHR | Fellows recruit | TALMA HQ events |  | Social Media Advertising |  | Pedagogical Content | Government Relationships | Cooperation between Resource Departments | DAM tool Implementation
Alumni | Ministry of Science | FY events | Compliance |  |  |  | PD | Foundations | Improve Professional Skills | Compliance
Annual Budget | Ministry of Education | Local Authorities | Office Renovation |  |  |  | Summer Program | General Fundraising | Recruitment | TALMA Curriculum App
Assessment | Gefen Projects | Housing for Fellows | Office Maintenance |  |  |  | WeSpeak | Business Partnerships | Conference - JEA | Google Drive
Bi-Lingual Ganim | Sderot | PD - TALMA Tuesday | Formal Employee Feedback |  |  |  | Practice Pal | Organizational Partnerships | Newsletters | Monday.com Implementation
Bi-Lingual Schools | Budget Management | PD - General | Conference / Event Management |  |  |  | Ness Ziona | TALMA Academy | Team Evaluations | Practice Pal
Bnei Ayish | Internal Audit | Fellow Development | Onboarding |  |  |  | Kiryat Shmona | Municipalities | Summer Program | Recruitment System
Bnot Sherut | Volunteers Report |  | Offboarding |  |  |  | Merhavim | Develop new municipalties | Full Year | Slack Implementation
Budget Management | Additional Report | [5 empty] | Debate Course | Strengthen existing municipalties | Summer Program | TALMA.digital
Business Partnerships | Payroll Process | [5 empty] | TALMA Games | TALMA Events - Annual Conference | Conference - Gala 2027 | TALMAisrael.com website
Compliance | Pensions | [5 empty] | Curriculum Database | Educator Communities | Conferences - General
Conference - Gala 2027 | Internal Financial System | [5 empty] | Bi-Lingual Ganim |  | Measurement/Assessment
Conference - JEA | Monthly Budget | [5 empty] | Bi-Lingual Schools |  | Represent TALMA at Events
Conference - JFN | Annual Budget | [5 empty] | Assessment |  | Networking
Conference - Prizmah | Profit Center and Cost Allocation Model | [5 empty] | Conferences - General |  | Grants
Conference / Event Management | Organizational Profitability | [5 empty] | TALMA Events - Kfar Azza |  | Conference - JFN
Conferences - General | [6 empty] | TALMA Events - Ministry of Labor |  | Conference - Prizmah
Cooperation between Resource Departments | [6 empty] | Ministry of Labor
Curriculum Database | [6 empty] | Bnot Sherut
DAM tool Implementation | [6 empty] | Evaluation - Internal
Debate Course | [6 empty] | Evaluation - Educational Impact
Develop new municipalties | [6 empty] | Evaluation - Reporting to External people
Educator Communities | [6 empty] | Evaluation - Collecting Data from Leaders about TALMA
Evaluation - Collecting Data from Leaders about TALMA | [6 empty] | Aharai
Evaluation - Educational Impact | [6 empty] | Kiryat Shmona
Evaluation - Internal
Evaluation - Reporting to External people
Fellow Development
Fellows recruit
Formal Employee Feedback
Foundations
Full Year
FY events
FY management
Gefen Projects
General Fundraising
Google Drive
Government Relationships
Grants
Housing for Fellows
Improve Professional Skills
Interdepartment Communication
Internal Audit
Internal Financial System
Kiryat Shmona
Local Authorities
Measurement/Assessment
Merhavim
Ministry of Education
Ministry of Labor
Ministry of Science
Monday.com Implementation
Monthly Budget
Municipalities
MyHR
Ness Ziona
Networking
Newsletters
Offboarding
Office Maintenance
Office Renovation
Onboarding
Organizational Partnerships
Organizational Profitability
Payroll Process
PD
PD - General
PD - TALMA Tuesday
Pedagogical Content
Pensions
Practice Pal
Profit Center and Cost Allocation Model
Recruitment
Recruitment System
Represent TALMA at Events
Sderot
Slack Implementation
Social Media Advertising
Strengthen existing municipalties
Summer Program
TALMA Academy
TALMA Curriculum App
TALMA Events - Annual Conference
TALMA Events - Kfar Azza
TALMA Events - Ministry of Labor
TALMA Events - Ministry of Science
TALMA Games
TALMA HQ events
TALMA.digital
TALMAisrael.com website
Team Evaluations
Volunteers Report
Website Advertising
WeSpeak

## Terms
status | priority | departments | quarters | strategic goals | people
Not Started | Critical | Finances | Q1 | Academic Status | Adi
Planned | High | Full Year | Q2 | Financial Independence | Daniel
In Progress | Medium | HR | Q3 | Impact Measurement | Debra
Done | Low | Management | Q4 | International Presence | Etelle
On Hold |  | Marketing |  | National Recognition | Ido Dvir
Blocked |  | Operations |  | Sustainable Growth | Ido M.
|  | Pedagogy |  |  | Jennifer
|  | Resources - Israel |  |  | Leila
|  | Resources - USA |  |  | Maayan
|  | Tech |  |  | Miri
Olga
Sarah
Shani
Shay
Sivan
Stacey
T'helah
Yael
Yuval
Jenna

## Pedagogy
TALMA Strategic Objective | Department Objective | Focus Area | Task Name | KPI | Status | Priority | Primary Owner / Main Responsible | Start Date | End Date | Quarter | Partners / Supporters | Cross-Department Collaboration | Estimated Budget | Notes
Sustainable Growth | Improve communication and collaboration | Interdepartment Communication | Identify and confirm upcoming partnerships and collaborations with other TALMA departments. | 1/ month | In Progress | High | Etelle |  | 2026-01-01 | Q1 |  | Resources - USA, Resources - Israel |  | 1) Map existing and potential collaborations across departments. 2) Hold 2-3 coordination meetings with the Development Department to align priorities and upcoming projects.
Impact Measurement | Evaluate and Measure TALMA programs | Full Year, Evaluation - Educational Impact | Conduct beginning-of-year student assessments, including learning and implementation across schools. |  | In Progress | Medium | Stacey |  | 2025-12-05 | Q1 | Jennifer | Tech, Full Year |  | 1) Collect and analyze assessment data from schools. 2) Present findings to identify instructional priorities. | הערכה ומדידה של התלמידים
Impact Measurement | Evaluate and Measure TALMA programs | TALMA.digital, Full Year | Develop a basic digital student assessment method based on the existing assessment framework. |  | Planned | Medium | Stacey |  | 2026-02-01 | Q1 | Daniel | Tech |  | Goal: Pilot digital tool in Ashkelon, Sderot and Eilat schools. 1) Define indicators and structure, build pilot tool 2) Train teachers on use 3) Collect data and feedback
National Recognition |  | TALMA Events - Kfar Azza | Plan |  | Done | High | Etelle |  | 2025-11-11 | Q1 | Ido | Finances |  | Goal: Fair held successfully on Nov 11 with approx 200+ Kfar Aza students participating and 30-40 volunteers
National Recognition |  | TALMA Events - Kfar Azza | Deliver |  | Done | High | Etelle |  | 2025-11-11 | Q1 | Ido | Finances |  | Goal: Fair held successfully on Nov 11 with approx 200+ Kfar Aza students participating and 30-40 volunteers
National Recognition |  | TALMA Events - Ministry of Labor, Ministry of Labor | Plan |  | In Progress | Critical | Etelle |  | 2025-12-07 | Q1 | Shani | Resources - Israel |  | 1) Draft the data outline for the project presentation by Nov 10. 2) Prepare visuals and PowerPoint presentation by Dec 1, and conduct at least one internal run-through before the conference.
National Recognition |  | TALMA Events - Ministry of Labor, Ministry of Labor | Deliver
Sustainable Growth | Improve communication and collaboration | Interdepartment Communication | Create strong connections between the pedagogy team, regional directors, and fellows. | 1/month | In Progress | Medium | Jennifer |  | 2025-12-31 | Q1 | Leila | Full Year |  | 1) Hold at least 2 alignment meetings with regional directors to ensure relevance. 2) Collect feedback from the regional directors (& teacher-leaders?) on clarity and applicability of PD content by Dec 15.
| Strengthen Professional Development | Full Year, PD - TALMA Tuesday | TALMA Tuesday Curriclum - Plan
| Strengthen Professional Development | Full Year, PD - TALMA Tuesday | TALMA Tuesday Curriclum - Deliver
| Strengthen Professional Development | Full Year, PD - TALMA Tuesday | Full Year PD Syllabus - Monthly updates and planning | 1 / month |  |  | Etelle, Miri
Sustainable Growth | Strengthen Professional Development | WeSpeak, PD | Write PD Materials |  | In Progress | Medium | Jennifer |  | 2025-11-30 | Q1 | Leila | Resources - Israel, Tech, Full Year |  | 1) Write 9th grade session plans 2) Recruit 15-20 teachers who don't teach "We Speak" (total of 40 teachers) 3) Develop 9 teacher training sessions
Sustainable Growth | Create and Deliver Pedagogical Content | WeSpeak, Pedagogical Content | Write curriculum for all grades
Sustainable Growth | Create and Deliver Pedagogical Content | Ministry of Labor, PD | Write the curriculum |  | In Progress | Medium | Stacey |  | 2025-12-15 | Q1 | Etelle | Resources - Israel, Tech |  | - Create, edit, and upload courses for the Ministry of Labor - Upload final versions to cefr.co.il - Ensure that tests, course providers, and communication between centers and providers operate smoothly
Sustainable Growth | Create and Deliver Pedagogical Content | Ministry of Labor, PD | Upload curriculum to CEFR website |  | In Progress | Medium | Stacey |  | 2025-12-15 | Q1 | Etelle | Resources - Israel, Tech |  | - Create, edit, and upload courses for the Ministry of Labor - Upload final versions to cefr.co.il - Ensure that tests, course providers, and communication between centers and providers operate smoothly
Academic Status | Strengthen Professional Development | PD, Bi-Lingual Ganim | Schedule the next Bilingual Ganim professional development session. |  | Planned | Medium | Stacey |  | 2025-12-15 | Q1 |  | Resources - Israel
Sustainable Growth | Strengthen Professional Development | PD, Bnot Sherut | Provide professional development for the Bnot Sherut and deliver at least three training sessions. |  | Planned | Medium | Jennifer |  | 2025-12-15 | Q1 | Leila
Impact Measurement | Evaluate and Measure TALMA programs | Bi-Lingual Ganim | Document and evaluate the Bi-Lingual Ganim in Sderot - with Multi |  | Not Started | Medium | Etelle |  | 2025-12-24 | Q1 | Stacey | Resources - Israel |  | Document and evaluate all activities by collecting feedback from Yifat, the Ganim teachers, and the Bnot Sherut, and summarize insights and recommended next steps for Q2.
Impact Measurement | Evaluate and Measure TALMA programs | Bnot Sherut | Document and evaluate the Bnot Sherut program Sderot - with end of program survey
Sustainable Growth | Create and Deliver Pedagogical Content | Merhavim, Pedagogical Content | Create content for Debate course |  | In Progress | Medium | Leila |  | 2025-12-15 | Q1 |  |  |  | - Write syllabus and lesson plans - Train teachers (1 zoom session) + record it for teachers who will join in the future
Sustainable Growth | Create and Deliver Pedagogical Content | Practice Pal, WeSpeak | Finalize Practice Pal games for WeSpeak program |  | In Progress | Medium | Leila |  | 2025-12-24 | Q1 | Jennifer | Resources - Israel, Tech |  | Design the digital platform features, align content with program pedagogy, create user-friendly training materials for educators
Sustainable Growth | Strengthen Professional Development | WeSpeak, PD | Lead PD sessions on Practice Pal for WeSpeak teachers
Sustainable Growth | Hire and retain high-quality teachers effectively | Recruitment | Work with Maayan to organize recruitment process |  | Planned | Critical | Etelle |  |  | Q2 |  | HR |  | 1) Develop outreach materials and a targeted recruitment strategy to attract strong candidates. 2) Create and implement an onboarding process that includes orientation & pedagogical training.
National Recognition | Evaluate and Measure TALMA programs | Ministry of Labor | Distribute certificates to students who complete the course |  | Not Started | Medium | Stacey |  | 2026-01-18 | Q2 | Etelle | Resources - Israel |  | הפקת תעודות ולתת מבחנים ולדאוג שיבצעו (דרך מעראכת של speak now)
Impact Measurement | Evaluate and Measure TALMA programs | Ministry of Labor, Evaluation - Educational Impact | Assess the students who finished the program (using SpeakNow system) |  | Not Started | Medium | Stacey |  | 2026-01-18 | Q2 | Etelle | Resources - Israel |  | הפקת תעודות ולתת מבחנים ולדאוג שיבצעו (דרך מעראכת של speak now)
Impact Measurement | Evaluate and Measure TALMA programs | Full Year, Evaluation - Internal | Mid-Year Class Observations (Full Year) - plan |  | Not Started | High | Leila |  |  | Q2 | Jennifer | Full Year |  | 1) Coordinate observation schedules with fellows. 2) Conduct classroom observations across all locations. 3) Document findings using the standardized observation form. 4) Provide individualized feedback to fellows following each observation. 5) Identify common needs for upcoming PD sessions.
Impact Measurement | Evaluate and Measure TALMA programs | Full Year, Evaluation - Internal | Mid-Year Class Observations (Full Year) - schedule
Impact Measurement | Evaluate and Measure TALMA programs | Full Year, Evaluation - Internal | Mid-Year Class Observations (Full Year) - deliver
Impact Measurement | Evaluate and Measure TALMA programs | Full Year, Evaluation - Internal | Mid-Year Class Observations (Full Year) - followup
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Bnei Ayish | Formal feedback (Bnei Ayish) - schedule |  | Planned | Low | Stacey |  | 2026-01-01 | Q2 |  |  |  | 1) Collect and analyze student work samples from each class prior to the mid-year meetings. 2) Develop a short action plan with each teacher based on identified needs.
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Bnei Ayish | Formal feedback (Bnei Ayish) - deliver
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Bnei Ayish | Formal feedback (Bnei Ayish) - followup
Impact Measurement | Improve communication and collaboration | Bi-Lingual Ganim | Conduct mid-year status check - Bilingual Ganim (Sderot) |  | Planned | High | Etelle |  | 2026-01-01 | Q2 | Stacey | Resources - Israel, Full Year |  | 1) Review the implementation of the pedagogical tools and document gaps or inconsistencies. 2) Draft a mid-year evaluation report with key insights, challenges, and recommended adjustments for Semester B.
|  | Bnot Sherut | Conduct mid-year status check - Bnot Sherut (Sderot)
|  | Full Year | Conduct mid-year status check - Full Year (Sderot)
Impact Measurement | Improve communication and collaboration | Aharai | Conduct mid-year status check - Aharai
Impact Measurement | Improve communication and collaboration | Ness Ziona | Conduct mid-year status check - Ness Ziona
Impact Measurement | Improve communication and collaboration | Merhavim | Conduct mid-year status check - Merhavim
Impact Measurement | Improve communication and collaboration | Kiryat Shmona | Conduct mid-year status check - Kiryat Shmona
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, WeSpeak | Mid-Year Class Observations (WeSpeak) - plan |  | Planned | High | Leila |  | 2026-01-01 | Q2 | Jennifer | Resources - Israel |  | 1) Coordinate observation schedules with fellows. 2) Conduct classroom observations across all locations. 3) Document findings using the standardized observation form. 4) Provide individualized feedback to fellows following each observation. 5) Identify common needs for upcoming PD sessions.
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, WeSpeak | Mid-Year Class Observations (WeSpeak) - schedule |  | Planned | High | Leila |  | 2026-01-01 | Q2 | Jennifer | Resources - Israel
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, WeSpeak | Mid-Year Class Observations (WeSpeak) - deliver |  | Planned | High | Leila |  | 2026-01-01 | Q2 | Jennifer | Resources - Israel
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, WeSpeak | Mid-Year Class Observations (WeSpeak) - followup |  | Planned | High | Leila |  | 2026-01-01 | Q2 | Jennifer | Resources - Israel
Academic Status | Developing, expanding, and solidifying English programs | TALMA Curriculum App | Plan and design the platform |  | Planned | Low | Etelle |  | 2026-02-01 | Q2 | Leila | Tech |  | 1) Map existing pedagogical content to identify structure, gaps, and duplication. 2) Draft an outline for the database architecture, including categories, tagging system, user permissions, and workflow for ongoing updates.
Sustainable Growth | Improve Professional Skills | Improve Professional Skills | Search for professional development sessions/opportunities for the pedagogy team, focusing on new trends and learnings from conferences or research. |  | Not Started | Low | Etelle |  | 2026-02-15 | Q2 | Jennifer | Finances |  | Create a shortlist of recommended PD options and present them to the pedagogy team with rationale, expected outcomes, and suggested participants
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Full Year | End-of-year feedback (full-year) - for fellows, regional directors, and Sivan - plan |  | Not Started | Medium | Jennifer |  | 2026-05-20 | Q3 | Leila | Full Year |  | 1) Distribute end-of-year feedback surveys/interviews for fellows, regional directors, and Sivan to gather insights on program quality and support. 2) Analyze responses and write feedback report highlighting trends, successes, and areas for improvement for the next year.
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Full Year | End-of-year feedback (full-year) - for fellows, regional directors, and Sivan - deliver
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Full Year | End-of-year feedback (full-year) - for fellows, regional directors, and Sivan - followup
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, WeSpeak | End-of-year feedback (WeSpeak) from teachers - plan |  | Not Started | Medium | Etelle |  | 2026-05-20 | Q3 | Stacey | Tech |  | 1) Develop and administer feedback questionnaires for Bnot Sherut and We Speak teachers to evaluate their training experience and professional growth. 2) Synthesize insights into a summary report outlining strengths, challenges, and recommendations for improving our training model.
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, WeSpeak | End-of-year feedback (WeSpeak) from teachers - deliver
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, WeSpeak | End-of-year feedback (WeSpeak) from teachers - followup
Impact Measurement | Evaluate and Measure TALMA programs | Bnot Sherut, Evaluation - Internal | End-of-year feedback (Bnot Sherut - sderot) - plan
Impact Measurement | Evaluate and Measure TALMA programs | Bnot Sherut, Evaluation - Internal | End-of-year feedback (Bnot Sherut - sderot) - deliver
Impact Measurement | Evaluate and Measure TALMA programs | Bnot Sherut, Evaluation - Internal | End-of-year feedback (Bnot Sherut - sderot) - followup
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Bi-Lingual Ganim | End-of-year feedback (Bilingual Ganim - sderot) - plan
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Bi-Lingual Ganim | End-of-year feedback (Bilingual Ganim - sderot) - deliver
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, Bi-Lingual Ganim | End-of-year feedback (Bilingual Ganim - sderot) - followup
Sustainable Growth | Evaluate and Measure TALMA programs | Evaluation - Internal | Collect and analyze end-of-year feedback and plan improvements for TALMA’s second year in Sderot. |  | Not Started | Medium | Etelle |  | 2026-05-20 | Q3 |  | Resources - Israel, Full Year
Sustainable Growth | Create and Deliver Pedagogical Content | Summer Program | Orientation - Plan |  | Not Started | Medium | Leila |  | 2026-06-01 | Q3 | Stacey | Resources - USA |  | 1) Coordinate with the U.S. recruitment team to ensure alignment between program needs, content updates, and candidate profiles. 2) Develop and organize all summer program materials (curriculum packets, training guides, classroom kits).
Sustainable Growth | Create and Deliver Pedagogical Content | Summer Program | Orientation - Deliver
Sustainable Growth | Create and Deliver Pedagogical Content | Summer Program, Pedagogical Content | Create content
Sustainable Growth | Create and Deliver Pedagogical Content | Merhavim | Debate - build the curriculum |  | Not Started | Medium | Etelle |  | 2026-05-20 | Q3 | Stacey | Resources - Israel |  | 1) Gather participation, performance, and engagement data from the current Debate Course cohorts (observations, teacher feedback, student outputs). 2) Analyze trends and identify conditions for success to create a data-based recommendation for expanding the to additional centers next year. | לבנות תכנים לתוכנית מרחבים, להריץ אותו בפיילוט, לאסוף עליו מידע ומשם לשכפל אותו לעוד מקומות
Sustainable Growth | Create and Deliver Pedagogical Content | Merhavim | Debate - deliver the program
Sustainable Growth | Create and Deliver Pedagogical Content | Merhavim | Debate - receive feedback from the teachers
Impact Measurement | Evaluate and Measure TALMA programs | Evaluation - Internal, TALMA.digital | Further develop and test the digital assessment system, integrating feedback from the beginning and mid-year implementations. |  | Not Started | Medium | Stacey |  | 2026-05-20 | Q3 | Etelle | Tech |  | Refine the digital assessment workflows (scoring, reporting, dashboards).
Sustainable Growth | Evaluate and Measure TALMA programs | Evaluation - Internal, WeSpeak | Update “We Speak” curriculum based on teacher feedback + assessment results, plan adjustments for future implementation in other programs. |  | Not Started | Low | Leila |  | 2026-06-01 | Q3 | Jennifer | Resources - Israel
Sustainable Growth | Strengthen Professional Development | Summer Program | Support the Summer Fellowship by sending pedagogy team members to conduct school visits, provide mentoring, and assist teachers on the ground |  | Not Started | High | Leila |  | 2026-07-01 | Q4 | Stacey | Resources - USA
Sustainable Growth | Create and Deliver Pedagogical Content | Evaluation - Internal | Create Sderot Year 2 Strategic Plan, according to the feedback |  | Not Started | Medium | Etelle |  | 2026-07-31 | Q4 |  | Resources - Israel
Sustainable Growth | Create and Deliver Pedagogical Content | Full Year, PD | Orientation - Planning |  | Not Started | High | Jennifer |  | 2026-07-15 | Q4 | Leila | Full Year
Sustainable Growth | Strengthen Professional Development | Full Year, PD | Orientation - Deliver |  | Not Started | High | Jennifer |  | 2026-07-15 | Q4 | Leila | Full Year
Sustainable Growth | Create and Deliver Pedagogical Content | PD, Full Year | Create Full Year 26-27 PD Plan, according to the feedback |  | Not Started | Medium | Jennifer |  | 2026-07-31 | Q4 | Leila | Full Year
Sustainable Growth | Developing, expanding, and solidifying English programs | Practice Pal | Begin developing content for a potential TALMA digital platform, with the goal of reducing reliance on outsourcing. |  | On Hold | Low | Leila |  | 2026-08-20 | Q4 | Daniel | Full Year, Tech |  | Explore the possibility of piloting the digital tool in selected schools, integrating it into full-year teacher practice and gathering data on its effectiveness.

## Resources - USA
TALMA Strategic Objective | Department Objective | Focus Area | Task Name | KPI | Status | Priority | Primary Owner / Main Responsible | Start Date | End Date | Quarter | Partners / Supporters | Cross-Department Collaboration | Estimated Budget | Notes
International Presence | Coordinate alumni events | Alumni | Virtual Event 1 - Plan |  | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni | Virtual Event 1 - Host |  | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni | Virtual Event 2 - Plan |  | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni | Virtual Event 2 - host |  | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni |  |  | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni | NYC event with regional Alumni Ambassador - Plan | 1 per quarter | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni | NYC event with regional Alumni Ambassador - Deliver | 1 per quarter | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni | DC event with regional Alumni Ambassador - Plan | 1 per quarter | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni | NYC event with regional Alumni Ambassador - Deliver | 1 per quarter | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
International Presence | Coordinate alumni events | Alumni |  |  | Not Started | Medium | Jenna |  | 2026-03-31 | Q1 | Finances | Finances
Sustainable Growth | Cooperation between Resource Departments | Cooperation between Resource Departments | Weekly Meeting with Resources - Israel | 1 per week | Not Started | Critical | T'helah |  | 2026-03-31 | Q1 | Resources - Israel | Resources - Israel
Financial Independence | Improve Professional Skills | Improve Professional Skills | Engage in the Jewish Digital Summit together with the US team |  | Planned | Critical | T'helah |  | 2026-01-02 | Q1 | Finances | Finances
Financial Independence | Improve Professional Skills | Improve Professional Skills | Take an Introduction to Effective Digital Fundraising course |  | Planned | Critical | T'helah |  | 2026-02-19 | Q1 | Finances | Finances
Financial Independence | Improve Professional Skills | Improve Professional Skills | Register for at least two standalone webinars and/or one course |  | Not Started | Critical | T'helah |  | 2026-09-30 | Q3 | Finances | Finances
Financial Independence | Improve Professional Skills | Improve Professional Skills | Register for at least two standalone webinars and/or one course |  | Not Started | Critical | T'helah |  | 2026-12-31 | Q4 | Finances | Finances
Sustainable Growth | Recruit teachers | Recruitment | Recruit Teachers to Summer Fellowship | 60 teachers for Summer | In Progress | Critical | T'helah |  | 2026-03-31 | Q1 | Full Year, Pedagogy, Resources - Israel | Full Year, Pedagogy, Resources - Israel
Sustainable Growth | Recruit teachers | Recruitment | Recruit teachers to full year fellowship | 5 teachers for Full Year | In Progress | Critical | T'helah |  | 2026-03-31 | Q1 | Full Year, Pedagogy, Resources - Israel | Full Year, Pedagogy, Resources - Israel
International Presence | Represent TALMA at Events | Conference - JEA | JEA - Planning |  | In Progress | Medium | T'helah |  | 2026-02-28 | Q1 | Finances, Pedagogy | Finances
International Presence | Represent TALMA at Events | Conference - JEA | JEA - Followup | Connect with all sign-ups on LinkedIn two weeks after the conference | In Progress | Medium | T'helah |  | 2026-02-28 | Q1 | Finances, Pedagogy | Finances
International Presence | Send Newsletters | Newsletters, Alumni | NYC alumni newsletter - send |  | Not Started | Low | Jenna |  | 2026-03-31 | Q1 | Full Year | Full Year
International Presence | Send Newsletters | Newsletters, Alumni | NYC alumni newsletter - track | - click rate of >= 3%, open rate >= 28% | Not Started | Low | Jenna |  | 2026-03-31 | Q1 | Full Year | Full Year
International Presence | Send Newsletters | Newsletters, Alumni | DC alumni newsletter - send |  | Not Started | Low | Jenna |  | 2026-03-31 | Q1 | Full Year | Full Year
International Presence | Send Newsletters | Newsletters, Alumni | DC alumni newsletter - track | - click rate of >= 3%, open rate >= 28% | Not Started | Low | Jenna |  | 2026-03-31 | Q1 | Full Year | Full Year
International Presence | Send Newsletters | Newsletters, Alumni | LA alumni newsletter - send |  | Not Started | Low | Jenna |  | 2026-03-31 | Q1 | Full Year | Full Year
International Presence | Send Newsletters | Newsletters, Alumni | LA alumni newsletter - track | - click rate of >= 3%, open rate >= 28% | Not Started | Low | Jenna |  | 2026-03-31 | Q1 | Full Year | Full Year
Sustainable Growth | Send Newsletters | Newsletters, Full Year | FYF newsletter to the FYF sign up list - send |  | Not Started | High | Adi |  | 2026-02-28 | Q1 | Full Year | Full Year
Sustainable Growth | Send Newsletters | Newsletters, Full Year | FYF newsletter to the FYF sign up list - track | - click rate of >= 3%, open rate >= 28% | Not Started | High | Adi |  | 2026-02-28 | Q1 | Full Year | Full Year
International Presence | Send Newsletters | Newsletters | Send Q2 General Newsletter (Purim) - send |  | Not Started | Medium | Adi |  | 2026-03-31 | Q2 | Resources - Israel, Full Year | Resources - Israel, Full Year
International Presence | Send Newsletters | Newsletters | Send Q2 General Newsletter (Purim) - track | - click rate of >= 3%, open rate >= 28% | Not Started | Medium | Adi |  | 2026-03-31 | Q2 | Resources - Israel, Full Year | Resources - Israel, Full Year
International Presence | Send Newsletters | Newsletters | Send Q3 General Newsletter (Chaggim) - send |  | Not Started | Medium | Adi |  | 2026-03-31 | Q3 | Resources - Israel, Full Year | Resources - Israel, Full Year
International Presence | Send Newsletters | Newsletters | Send Q3 General Newsletter (Chaggim) - track | - click rate of >= 3%, open rate >= 28% | Not Started | Medium | Adi |  | 2026-03-31 | Q3 | Resources - Israel, Full Year | Resources - Israel, Full Year
International Presence | Send Newsletters | Newsletters | Send Q1 General Newsletter (Channukah) - send |  | Not Started | Medium | Adi |  | 2026-03-31 | Q1 | Resources - Israel, Full Year | Resources - Israel, Full Year
International Presence | Send Newsletters | Newsletters | Send Q1 General Newsletter (Channukah) - track | - click rate of >= 3%, open rate >= 28% | Not Started | Medium | Adi |  | 2026-03-31 | Q1 | Resources - Israel, Full Year | Resources - Israel, Full Year
Impact Measurement | Conduct Team Evaluations Feedback | Team Evaluations | Formal Progress Review (June) - Adi |  | Not Started | High | T'helah |  | 2026-06-30 | Q2 | HR | HR
Impact Measurement | Conduct Team Evaluations Feedback | Team Evaluations | Formal Progress Review (End of Year) - Adi |  | Not Started | High | T'helah |  | 2026-11-30 | Q4 | HR | HR
Impact Measurement | Conduct Team Evaluations Feedback | Team Evaluations | Formal Progress Review (June) - Jenna |  | Not Started | High | T'helah |  | 2026-06-30 | Q2 | HR | HR
Impact Measurement | Conduct Team Evaluations Feedback | Team Evaluations | Formal Progress Review (End of Year) - Jenna |  | Not Started | High | T'helah |  | 2026-11-30 | Q4 | HR | HR
Sustainable Growth | Manage Fellowship administration | Summer Program | Submit Taglitom itinerary |  | Not Started | High | T'helah |  | 2026-05-31 | Q2 | Pedagogy | Pedagogy, Resources - Israel, Finances
Sustainable Growth | Manage Fellowship administration | Summer Program | Submit health insurance details to Eishonim |  | In Progress | High | T'helah |  | 2026-05-31 | Q2 | Resources - Israel | Pedagogy, Resources - Israel, Finances
Sustainable Growth | Manage Fellowship administration | Summer Program | Assign Summer Fellow placements & roommates |  | Not Started | High | T'helah |  | 2026-06-05 | Q2 | Resources - Israel, Finances | Pedagogy, Resources - Israel, Finances
Sustainable Growth | Manage Fellowship administration | Summer Program | Arrange flights for all Summer Fellows |  | In Progress | High | T'helah |  | 2026-06-12 | Q2 | Resources - Israel, Finances | Pedagogy, Resources - Israel, Finances
Sustainable Growth | Manage Fellowship administration | Summer Program | Collect background checks from all male Fellows |  | In Progress | High | T'helah |  | 2026-06-18 | Q2 | Pedagogy, Resources - Israel, Finances | Pedagogy, Resources - Israel, Finances
Sustainable Growth | Manage Fellowship administration | Full Year | Collect background checks from all male Fellows |  | In Progress | High | T'helah |  | 2026-06-18 | Q2 | Pedagogy, Resources - Israel, Finances | Pedagogy, Resources - Israel, Finances
Impact Measurement | Manage Fellowship administration | Summer Program, Measurement/Assessment | Administer end of program survey |  | Not Started | High | T'helah |  | 2026-06-30 | Q2 | Pedagogy | Pedagogy, Resources - Israel
Impact Measurement | Manage Fellowship administration | Summer Program, Measurement/Assessment | Administer end of program survey |  | Not Started | High | T'helah |  | 2026-07-10 | Q3 | Pedagogy | Pedagogy, Resources - Israel
Impact Measurement | Manage Fellowship administration | Summer Program, Measurement/Assessment | Administer end of program survey |  | Not Started | High | T'helah |  | 2026-07-20 | Q3 | Pedagogy | Pedagogy, Resources - Israel
Impact Measurement | Manage Fellowship administration | Summer Program, Measurement/Assessment | Administer end of program survey |  | Not Started | High | T'helah |  | 2026-07-22 | Q3 | Pedagogy | Pedagogy, Resources - Israel
Sustainable Growth | Manage Fellowship administration | Summer Program | Arrange flights for all Full Year Fellows |  | In Progress | High | T'helah |  | 2026-08-13 | Q3 | Resources - Israel, Finances | Pedagogy, Resources - Israel, Finances
Sustainable Growth | Manage Fellowship administration | Summer Program | Produce internal Summer 2026 report |  | Not Started | High | T'helah |  | 2026-08-31 | Q3 |  | Pedagogy, Resources - Israel
Sustainable Growth | Manage Fellowship administration | Summer Program | Establish dates for 2027 and update registration documents |  | Not Started | High | T'helah |  | 2026-08-31 | Q3 |  | Pedagogy, Resources - Israel
Sustainable Growth | Send Newsletters | Summer Program | Highlights newsletter for Jewish day schools - plan |  | Not Started | High | T'helah |  | 2026-08-31 | Q3 | Resources - Israel, Tech | Pedagogy, Resources - Israel
Sustainable Growth | Send Newsletters | Summer Program | Highlights newsletter for Jewish day schools - execute |  | Not Started | High | T'helah |  | 2026-08-31 | Q3 | Resources - Israel, Tech | Pedagogy, Resources - Israel
Sustainable Growth | Manage Fellowship administration | Full Year | Launch applications for Full Year 2027-28 |  | Not Started | High | T'helah |  | 2026-09-14 | Q3 |  | Pedagogy, Resources - Israel
Sustainable Growth | Manage Fellowship administration | Summer Program | Launch applications for Summer 2027 |  | Not Started | High | T'helah |  | 2026-09-14 | Q3 |  | Pedagogy, Resources - Israel
Financial Independence | Represent TALMA at Events | Conference - Gala 2027 | Plan |  | Not Started | High | T'helah |  | 2026-03-31 | Q1 | Pedagogy, Resources - Israel, Finances, Tech, HR, Full Year | Pedagogy, Resources - Israel, Finances, Tech, HR, Full Year
Financial Independence | Represent TALMA at Events | Conference - Gala 2027 | Finalize Details |  | Not Started | High | T'helah |  | 2026-04-30 | Q2 | Pedagogy, Resources - Israel, Finances, Tech, HR, Full Year | Pedagogy, Resources - Israel, Finances, Tech, HR, Full Year
Financial Independence | Represent TALMA at Events | Conference - Gala 2027 | Deliver |  | Not Started | High | T'helah |  | 2026-06-30 | Q2 | Pedagogy, Resources - Israel, Finances, Tech, HR, Full Year, Marketing | Pedagogy, Resources - Israel, Finances, Tech, HR, Full Year
International Presence | Represent TALMA at Events | Conferences - General | Draft & submit 2027 conference plan & budget |  | Not Started | Medium | T'helah |  | 2026-09-30 | Q3 | Finances, Pedagogy | Finances, Pedagogy
International Presence | Recruit teachers | Summer Program | Message principals list & send out Summer Fellowship flyer |  | Planned | Medium | Adi |  | 2026-03-31 | Q1
International Presence | Present TALMA to educators | Networking | Meetings with Teacher Organizations | 10 per quarter | Planned | Medium | Adi |  | 2026-03-31 | Q1
Financial Independence | Raise funds | Grants | Apply for grants | 2 per quarter | Not Started | Critical | T'helah |  | 2026-03-31 | Q1 | Resources - Israel, Finances | Resources - Israel, Finances
Financial Independence | Raise funds | Grants | Analyze grant submissions for 2026 |  | Not Started | Critical | T'helah |  | 2026-12-31 | Q4 | Resources - Israel, Finances | Resources - Israel, Finances
Sustainable Growth | Recruit teachers | Summer Program | Recruit Teachers for Summer Program | 100 | In Progress | Critical | T'helah |  | 2026-05-31 | Q2 | Full Year, Pedagogy, Resources - Israel | Full Year, Pedagogy, Resources - Israel
Sustainable Growth | Recruit teachers | Full Year | Recruit Teachers for Full Year Fellowship | 12 | In Progress | Critical | T'helah |  | 2026-06-30 | Q2 | Full Year, Pedagogy, Resources - Israel | Full Year, Pedagogy, Resources - Israel
Sustainable Growth | Recruit teachers | Full Year | Recruit Teachers for Full Year Fellowship | 15 | In Progress | Critical | T'helah |  | 2026-07-31 | Q3 | Full Year, Pedagogy, Resources - Israel | Full Year, Pedagogy, Resources - Israel
International Presence | Represent TALMA at Events | Conference - JFN | JFN - Register TALMA Team |  | In Progress | Medium | T'helah |  | 2026-05-31 | Q2 | Finances | Pedagogy
International Presence | Represent TALMA at Events | Conference - JFN | JFN - Plan |  | In Progress | Medium | T'helah |  | 2026-08-31 | Q3 | Pedagogy | Pedagogy
International Presence | Represent TALMA at Events | Conference - JFN | JFN - Deliver |  | In Progress | Medium | T'helah |  | 2026-08-31 | Q3 | Pedagogy | Pedagogy
International Presence | Represent TALMA at Events | Conference - JFN | JFN - Followup |  | In Progress | Medium | Adi |  | 2026-11-24 | Q4
International Presence | Represent TALMA at Events | Conference - Prizmah | Prizmah - Signup |  | In Progress | Medium | T'helah |  | 2026-09-30 | Q3 | Finances | Pedagogy
International Presence | Represent TALMA at Events | Conference - Prizmah | Prizmah - Plan |  | In Progress | Medium | T'helah |  | 2026-09-30 | Q3 | Pedagogy | Pedagogy
International Presence | Represent TALMA at Events | Conference - Prizmah | Prizmah - Deliver |  | In Progress | Medium | T'helah |  | 2026-12-31 | Q4 | Pedagogy | Pedagogy
| Represent TALMA at Events | Conference - Prizmah | Prizmah - Followup
International Presence | Send Newsletters | Newsletters | General alumni newsletter - send |  | Not Started | Low | Jenna |  | 2026-03-31 | Q1 | Full Year | Full Year
Sustainable Growth | Send Newsletters | Newsletters | General alumni newsletter - track | - click rate of >= 3%, open rate >= 28% | Not Started | High | Jenna |  | 2026-05-31 | Q2 | Full Year | Full Year
Sustainable Growth | Coordinate alumni events | Alumni, Networking |  |  | Not Started | Medium | Jenna |  | 2026-08-31 | Q3 | Tech | Tech
Sustainable Growth | Recruit teachers | Full Year | Status Update - FY Recruitment | 1 / month | [9 empty] | Detail how much are in each stage of platform

## Full Year
TALMA Strategic Objective | Department Objective | Focus Area | Task Name | KPI | Status | Priority | Primary Owner / Main Responsible | Start Date | End Date | Quarter | Partners / Supporters | Cross-Department Collaboration | Estimated Budget | Notes
Sustainable Growth | Recruit teachers | Full Year, Recruitment | Publicize Call for Applicants (Monthly) | 1x month | Planned | High | T'helah |  | 2026-05-31 | Q1 | Marketing | HR |  | Publish call for applicants on platforms + coordinate with partners: Facebook, Instagram, Linkedin, Nefesh Benefesh Board, JEDLAB Jobs
| Recruit teachers | Full Year, Recruitment
Sustainable Growth | Recruit teachers | Full Year, Recruitment | Initial Zoom interview with T'helah – fit screening (Airtable) |  | Planned | High | T'helah |  | 2026-07-20 | Q1 | Pedagogy | HR
Sustainable Growth | Recruit teachers | Full Year, Recruitment | Pedagogical interview with program director + pedagogy team (Airtable) |  | Planned | High | Miri, Leila |  | 2026-07-20 | Q1 | Pedagogy | HR
Sustainable Growth | Recruit teachers | Full Year, Recruitment | Request and evaluate lesson plan + demo video (Airtable) |  | Planned | High |  |  | 2026-07-20 | Q1 | Pedagogy | HR
Sustainable Growth | Recruit teachers | Full Year, Recruitment | Send offer to approved fellows for 2026-27 (Airtable) |  | Planned | High |  |  | 2026-07-31 | Q1 | T'helah | HR
Sustainable Growth | Recruit teachers | Full Year | Move applicant to FY base on Airtable + track completion |  | Planned | High |  |  | 2026-07-31 | Q1 | T'helah | HR
Sustainable Growth | Recruit teachers | Full Year, Recruitment | Collect documents for Jewish Agency / B1 Visa (Airtable) |  | Planned | High |  |  | 2026-06-30 | Q1 | Full Year | HR
Sustainable Growth | Recruit teachers | Full Year, Recruitment | Coordinate visa approvals with Ministry of Interior |  | Planned | High |  |  | 2026-07-31 | Q1 | Full Year | HR
Sustainable Growth | Place Teachers | Full Year | Recieve data from R&D Dep. on which municipalities we will work in |  | Not Started |  | Shay, Miri |  | 2026-04-30 |  | R&D
Sustainable Growth | Place Teachers | Full Year | Recieve data from R&D Dep. how many fellows are required to each location |  | Not Started |  | Shay, Miri |  | 2026-05-30 |  | R&D
Sustainable Growth | Place Teachers | Full Year | Match candidates to regions based on background |  | Planned | High | Miri |  | 2026-06-30 | Q1 | Pedagogy | HR
Sustainable Growth | Place Teachers | Full Year | Recieve from the municipality a list of school we will place in |  |  |  | Miri |  | 2026-07-15 |  | Municipality
Sustainable Growth | Place Teachers | Full Year | Match candidates to schools based on pedagogical needs |  | Planned | High | Miri |  | 2026-07-31 | Q1 | Pedagogy | HR
Sustainable Growth | Recruitment & Housing | Full Year | Find apartments (shared/individual) per municipality |  | Planned | High | Miri |  | 2026-05-31 | Q1 | Regional director | HR
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Map apartment needs - Eilat |  |  | High | Miri, Debra |  | 2026-05-31 | Q1 | Regional director | HR
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Find apartments - Eilat |  |  |  | Miri, Debra
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Verify apartment furnishing and equipment - Eilat |  |  |  | Miri, Debra
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Map apartment needs - Sderot |  |  | High | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Find apartments - Sderot |  |  |  | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Verify apartment furnishing and equipment - Sderot |  |  |  | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Map apartment needs - Jlem/BS |  |  | High | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Find apartments - Jlem/BS |  |  |  | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Verify apartment furnishing and equipment - Jlem/BS |  |  |  | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Map apartment needs - Ashkelon |  |  |  | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Find apartments - Ashkelon |  |  |  | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Verify apartment furnishing and equipment - Ashkelon |  |  |  | Miri, Yael
Sustainable Growth | Find Housing for Fellows | Full Year, Housing for Fellows | Match roommates based on culture/religion/personal preference |  | Planned | High | Miri |  | 2026-07-20 | Q1 | HR | HR
Sustainable Growth | Recruitment & Housing | Full Year | Arrange flights with travel agency and confirm itineraries - for eligible fellows | המורים שולחים את כל הפרטים דרך איירטייבל ואני מעבירה לטרוולנד דרך גוגל שיטס משותף. טרוולנד שולחת את פרטי הטיסות ישירות אל המורים, אני לא מקבלת אותם. אני חושבת שסיוון הייתה מבקשת מכל אחד לשלוח לה תאריך/שעת נחיתה כדי שהיא תוכל לארגן הסעות | Planned | High |  |  | 2026-07-31 | Q1 | T'helah | HR
Sustainable Growth | Recruitment & Housing | Full Year | Recieve flight chart info from T'helah - landing times for orientation |  | Planned | High |  |  | 2026-08-09 | Q1 | T'helah | HR
Impact Measurement | Routine Follow-up | Full Year | 4 days of weekly co-teaching |  | In Progress | Medium |  |  | 2026-08-31 | Q1 | Pedagogy | Full Year
Impact Measurement | Lead TALMA Tuesday Sessions | Full Year | TALMA Tuesday PD - TALMA Tuesday: Pedagogy+Hebrew sessions - Building cillabus | בנייה - פדגוגיה העברה - מנהלות אזור | In Progress | Medium |  |  | 2026-07-15 | Q1 | Pedagogy | Pedagogy
Sustainable Growth | Lead TALMA Tuesday Sessions | Full Year, PD - TALMA Tuesday | Plan annual schedule (GAANT) |  |  |  | Miri
Sustainable Growth | Lead TALMA Tuesday Sessions | Full Year, PD - TALMA Tuesday | Plan trips | 4 / year
Sustainable Growth | Lead TALMA Tuesday Sessions | Full Year, PD - TALMA Tuesday | TALMA Tuesday Status Update - Eilat | 1 / week (starting / ending when?) |  |  | Miri | [6 empty] | South, Eilat region, JLM&BS regions
Sustainable Growth | Lead TALMA Tuesday Sessions | Full Year, PD - TALMA Tuesday | TALMA Tuesday Status Update - Sderot & Ashkelon | 1 / week (starting / ending when?)
Sustainable Growth | Lead TALMA Tuesday Sessions | Full Year, PD - TALMA Tuesday | TALMA Tuesday Status Update - Jerusalem | 1 / week (starting / ending when?)
Sustainable Growth | Manage Routine Program Operations | Full Year | Teacher Leaders - offer the role to selected fellows (social and pedagogy leaders) |  | In Progress | Medium |  |  | 2026-07-15 |  | Pedagogy
Sustainable Growth | Manage Routine Program Operations | Full Year | Teacher Leaders - Monthly Meeting Status UPDATE | 1 / months (starting / ending when?) | Planned | Medium | Leila, Miri |  | 2026-09-30 |  | Regional directors
|  |  | Monthly Fellow Checkins - Status UPD - TALMA Tuesdayate | 1 / months (starting / ending when?) | [9 empty] | per region
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 1st semester - South region |  | Planned | Medium |  |  | 2026-11-30 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 1st semester - JLM&BS region |  | Planned | Medium |  |  | 2026-11-30 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 1st semester - Eilat region |  | Planned | Medium |  |  | 2026-11-30 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 2nd semester - South region |  | Planned | Medium |  |  | 2027-02-28 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 2nd semester - JLM&BS region |  | Planned | Medium |  |  | 2027-02-28 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 2nd semester - Eilat region |  | Planned | Medium |  |  | 2027-02-28 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 3rd semester - South region |  | Planned | Medium |  |  | 2027-06-11 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 3rd semester - JLM&BS region |  | Planned | Medium |  |  | 2027-06-11 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Track attendance + schedules - 3rd semester - Eilat region |  | Planned | Medium |  |  | 2027-06-11 | Q1 | Pedagogy | School Staff
Sustainable Growth | Support Fellows | Full Year, Fellow Development | Support for new fellows (map) - Eilat
Sustainable Growth | Support Fellows | Full Year, Fellow Development | Support for new fellows (map) - South
Sustainable Growth | Support Fellows | Full Year, Fellow Development | Support for new fellows (map) - Jlem / BS
Sustainable Growth | Support Fellows | Full Year, Fellow Development | Support for new fellows (followup) - Eilat | 1 per two months
Sustainable Growth | Support Fellows | Full Year, Fellow Development | Support for new fellows (followup) - South | 1 per two months
Sustainable Growth | Support Fellows | Full Year, Fellow Development | Support for new fellows (followup) - Jlem / BS | 1 per two months
Sustainable Growth | Support Fellows | Full Year | Support fellows with classroom challenges - South region | 1 / quarter | Not Started | Medium |  |  | 2026-10-31 | Q1 | Pedagogy | School Staff
Sustainable Growth | Support Fellows | Full Year | Support fellows with classroom challenges - JLM&BS | 1 / quarter | Not Started | Medium |  |  | 2026-10-31 | Q1 | Pedagogy | School Staff
Sustainable Growth | Support Fellows | Full Year | Support fellows with classroom challenges - Eilat | 1 / quarter | Not Started | Medium |  |  | 2026-10-31 | Q1 | Pedagogy | School Staff
Impact Measurement | Routine Follow-up | Full Year | Hold a meeting with the english-coordinator in each school - Sderot | 1 per two months | Not Started | Medium |  |  | 2026-10-31 | Q1 | School Staff | School Staff
Impact Measurement | Routine Follow-up | Full Year | Hold a meeting with the english-coordinator in each school - Ashkelon | 1 per two months | Not Started | Medium |  |  | 2026-10-31 | Q1 | School Staff | School Staff
Impact Measurement | Routine Follow-up | Full Year | Hold a meeting with the english-coordinator in each school - Kfar Aza | 1 per two months | Not Started | Medium |  |  | 2026-10-31 | Q1 | School Staff | School Staff
Impact Measurement | Routine Follow-up | Full Year | Hold a meeting with the english-coordinator in each school - JLM | 1 per two months | Not Started | Medium |  |  | 2026-10-31 | Q1 | School Staff | School Staff
Impact Measurement | Routine Follow-up | Full Year | Hold a meeting with the english-coordinator in each school - Ben Shemen | 1 per two months | Not Started | Medium |  |  | 2026-10-31 | Q1 | School Staff | School Staff
Impact Measurement | Routine Follow-up | Full Year | Hold a meeting with the english-coordinator in each school - Eilat | 1 per two months | Not Started | Medium |  |  | 2026-10-31 | Q1 | School Staff | School Staff
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 1 - schedule | [5 empty] | 2026-10-07 |  |  |  |  | *mandatory for all fellows* and document observation
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 1 - schedule | [5 empty] | 2026-10-07 |  |  |  |  | *mandatory for all fellows* and document observation
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 1 - schedule | [5 empty] | 2026-10-07 |  |  |  |  | *mandatory for all fellows* and document observation
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 1 - deliver | [5 empty] | 2026-10-31 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 1 - deliver | [5 empty] | 2026-10-31 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 1 - deliver | [5 empty] | 2026-10-31 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 1 - followup
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 1 - followup
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 1 - followup
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 2 - schedule | [5 empty] | 2026-11-12 |  |  |  |  | when needed (new fellows etc.)
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 2 - schedule | [5 empty] | 2026-11-12 |  |  |  |  | when needed (new fellows etc.)
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 2 - schedule | [5 empty] | 2026-11-12 |  |  |  |  | when needed (new fellows etc.)
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 2 - deliver | [5 empty] | 2026-12-15 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 2 - deliver | [5 empty] | 2026-12-15 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 2 - deliver | [5 empty] | 2026-12-15 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 2 - followup
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 2 - followup
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 2 - followup
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 3 - schedule | [5 empty] | 2027-01-31 |  |  |  |  | when needed (decide who needs)
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 3 - schedule | [5 empty] | 2027-01-31 |  |  |  |  | when needed (decide who needs)
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 3 - schedule | [5 empty] | 2027-01-31 |  |  |  |  | when needed (decide who needs)
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 3 - deliver | [5 empty] | 2027-02-28 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 3 - deliver | [5 empty] | 2027-02-28 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 3 - deliver | [5 empty] | 2027-02-28 |  |  |  |  | hold an immediate feedback in school with the fellow&document observation file
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Eilat) 3 - followup
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (South) 3 - followup
Sustainable Growth | Observation & Evaluation | Full Year, Evaluation - Internal | Class Observations (Jerusalem) 3 - followup
Impact Measurement | Observation & Evaluation | Full Year | Visit school - Hold principal + coordinator expectation meeting - Sderot | מירי, לשיקולך האם צריך להיות עוד ביקור בבית הספר בהכרח. יש בתי ספר שזה קורה באופן טבעי, השאלה אם חייב שוב. | Not Started | High |  |  | 2026-10-31 | Q2 | School Staff | Pedagogy
Impact Measurement | Observation & Evaluation | Full Year | Visit school - Hold principal + coordinator expectation meeting - Ashkelon |  | Not Started | High |  |  | 2026-10-31 | Q2 | School Staff | Pedagogy
Impact Measurement | Observation & Evaluation | Full Year | Visit school - Hold principal + coordinator expectation meeting - Kfar Aza |  | Not Started | High |  |  | 2026-10-31 | Q2 | School Staff | Pedagogy
Impact Measurement | Observation & Evaluation | Full Year | Visit school - Hold principal + coordinator expectation meeting - JLM |  | Not Started | High |  |  | 2026-10-31 | Q2 | School Staff | Pedagogy
Impact Measurement | Observation & Evaluation | Full Year | Visit school - Hold principal + coordinator expectation meeting - Ben Shemen |  | Not Started | High |  |  | 2026-10-31 | Q2 | School Staff | Pedagogy
Impact Measurement | Observation & Evaluation | Full Year | Visit school - Hold principal + coordinator expectation meeting - Eilat |  | Not Started | High |  |  | 2026-10-31 | Q2 | School Staff | Pedagogy
Impact Measurement | Observation & Evaluation | Full Year | Prepare mid-year goals document for each fellow before mid-year meetings - South region |  | Not Started | High |  |  | 2027-03-10 | Q2 | Pedagogy | Pedagogy
Impact Measurement | Observation & Evaluation | Full Year | Prepare mid-year goals document for each fellow before mid-year meetings - JLM&BS |  | Not Started | High |  |  | 2027-03-10 | Q2 | Pedagogy | Pedagogy
Impact Measurement | Observation & Evaluation | Full Year | Prepare mid-year goals document for each fellow before mid-year meetings - Eilat |  | Not Started | High |  |  | 2027-03-10 | Q2 | Pedagogy | Pedagogy
Sustainable Growth | Returners | Full Year | Send returners interest form for 2027-2028 |  | Planned | High |  |  | 2027-02-01 | Q2 | Pedagogy | Pedagogy
Sustainable Growth | Returners | Full Year | Hold a team meeting on returners - decisions after observations | [5 empty] | 2027-03-15 |  | Pedagogy
Sustainable Growth | Returners | Full Year | Schedule a personal meeting with each fellow who wish to return for another year - South region | each fellow |  |  |  |  | 2027-03-31 |  | Pedagogy
Sustainable Growth | Returners | Full Year | Schedule a personal meeting with each fellow who wish to return for another year - JLM&BS region | each fellow |  |  |  |  | 2027-03-31 |  | Pedagogy
Sustainable Growth | Returners | Full Year | Schedule a personal meeting with each fellow who wish to return for another year - Eilat region | each fellow |  |  |  |  | 2027-03-31 |  | Pedagogy
Sustainable Growth | Fellow Development | Full Year | Develop personalized goals for each fellow - including project and teaching routine based on cillabus |  | Planned | Medium |  |  | 2026-10-20 | Q2 | Pedagogy | Full Year
Sustainable Growth | Fellow Development | Full Year | Social monthly meeting - South region - yearly plan |  | Planned | Medium |  |  | 2026-09-30 | Q2 | Teacher Leaders | Full Year
Sustainable Growth | Fellow Development | Full Year | Social monthly meeting - JLM&BS region - yearly plan |  | Planned | Medium |  |  | 2026-09-30 | Q2 | Teacher Leaders | Full Year
Sustainable Growth | Fellow Development | Full Year | Social monthly meeting - Eilat region - yearly plan |  | Planned | Medium |  |  | 2026-09-30 | Q2 | Teacher Leaders | Full Year
Sustainable Growth | Fellow Development | Full Year | Social monthly meeting - South region - each month |  | Planned | Medium |  |  | 2026-09-30 | Q2 | Teacher Leaders | Full Year
Sustainable Growth | Fellow Development | Full Year | Social monthly meeting - JLM&BS region - each month |  | Planned | Medium |  |  | 2026-09-30 | Q2 | Teacher Leaders | Full Year
Sustainable Growth | Fellow Development | Full Year | Social monthly meeting - Eilat region - each month |  | Planned | Medium |  |  | 2026-09-30 | Q2 | Teacher Leaders | Full Year
Academic Status | Orientation & Onboarding | Full Year | Create Excel table of insured fellows |  | Planned | High |  |  | 2026-08-02 | Q3 | Full Year | Tech
Academic Status | Orientation & Onboarding | Full Year | Send Udelsman health insurance forms + passports of all insured fellows |  | Planned | High |  |  | 2026-08-09 | Q3 | Alon Udelsman | Tech
Academic Status | Orientation & Onboarding | Full Year | Activate health insurance policies and send fellows their policy number |  | Planned | High |  |  | 2026-08-13 | Q3 | Alon Udelsman | Tech
Academic Status | Orientation & Onboarding | Full Year | Arrange transportation from airport to orientation | לפני כן מנהלת שנתית מקבלת פרטי טיסה מכל עמית ואז מארגנת הסעות | Planned | High |  |  | 2026-08-10 | Q3 | Full Year | Tech
Academic Status | Orientation & Onboarding | Full Year | Arrange transportation from orientation to regions |  | Planned | High |  |  | 2026-08-10 | Q3 | Full Year | Tech
Academic Status | Orientation & Onboarding | Full Year | Prepare orientation agenda (week-long training) |  | Planned | High |  |  | 2026-06-30 | Q3 | Regional director | Tech
Academic Status | Orientation & Onboarding | Full Year | Pedagogy sessions for orientation | לוודא שנבנה - זו תת משימה... | Planned | High | Miri, T'helah |  | 2026-06-10 | Q3 | Pedagogy | Tech
Academic Status | Orientation & Onboarding | Full Year | Share pedagogical materials + teaching models - post orientation on email |  | Planned | High |  |  | 2026-08-26 | Q3 | Pedagogy | Tech
Academic Status | Orientation & Onboarding | Full Year | Train fellows in communication protocols with schools |  | Planned | High |  |  | August | Q3 | Pedagogy | Tech
Academic Status | Orientation & Onboarding | Full Year | Onboard fellows to HR system + login setup |  | Planned | High |  |  | August-September | Q3 | HR | Tech
Academic Status | Orientation & Onboarding | Full Year | Send Israeli contracts to citizens + track signature |  | Planned | High |  |  | August-post orientation | Q3 | HR | Tech
Academic Status | Orientation & Onboarding | Full Year | Provide arrival support at regional apartments | לכל אזור | Planned | High |  |  | August | Q3 | Full Year | Tech
Academic Status | School Collaboration Setup | Full Year | Hold kickoff meeting with principal + English coordinator and present to school full‑year structure and expectations - cillabus, projects etc. | ? | Planned | Medium |  |  | 2026-09-30 | Q3 | School Staff | School Staff
Academic Status | School Collaboration Setup | Full Year | Align weekly schedule and responsibilities |  | Planned | Medium |  |  | September | Q3 | Full Year | School Staff
Academic Status | School Collaboration Setup | Full Year | Review student demographics and school needs - During first meeting with school | מידע שצריך לעלות מהפגישה של מנהלת המוקד עם בתי הספר טרום השיבוצים | Planned | Medium |  |  | 2026-08-31 | Q3 | School Staff | School Staff
Academic Status | School Collaboration Setup | Full Year | Prepare English-speaking baseline plan |  | Planned | Medium |  |  | September | Q3 | Pedagogy | School Staff
Academic Status | School Collaboration Setup | Full Year | Conduct pre-test in all classrooms | לדייק | Planned | Medium |  |  | October | Q3 | Pedagogy | School Staff
Academic Status | School Collaboration Setup | Full Year | Analyze pre-test data for grouping | לדייק | Planned | Medium |  |  | October | Q3 | Pedagogy | School Staff
Academic Status | School Collaboration Setup | Full Year | Finalize teaching groups and levels | לדייק | Planned | Medium |  |  | October | Q3 | Full Year | School Staff
Academic Status | School Collaboration Setup | Full Year | Prepare materials to school for English speaking activities |  | Planned | Medium |  |  | October | Q3 | Pedagogy | School Staff
Academic Status | School Collaboration Setup | Full Year | UPD - TALMA Tuesdayate municipality with school needs and placements | per municipality / region | Planned | Medium |  |  | November | Q3 | Municipality | School Staff
Impact Measurement | End-Year Review | Full Year | Conduct post-test in classrooms | לדייק | Planned | High |  |  | May | Q4 | Pedagogy | Pedagogy
Impact Measurement | End-Year Review | Full Year | Collect and analyze student progress data | לדייק | Planned | High |  |  | May | Q4 | Full Year | Pedagogy
Impact Measurement | End-Year Review | Full Year | Hold end-year meeting with principal + coordinator | לכל בית ספר | Planned | High |  |  | June | Q4 | School Staff | Pedagogy
Impact Measurement | End-Year Review | Full Year | Prepare fellow continuation offers |  | Planned | High |  |  | May | Q4 | Pedagogy | Pedagogy
Impact Measurement | End-Year Review | Full Year | Conduct exit interviews for non-returning fellows |  | Planned | High |  |  | May | Q4 | Full Year | Pedagogy
Impact Measurement | End-Year Review | Full Year | Assemble end-year school report + recommendations | לכל בית ספר? | Planned | High |  |  |  | Q4 | Pedagogy | Pedagogy

## Finance
TALMA Strategic Objective | Department Objective | Focus Area | Task Name | KPI | Status | Priority | Primary Owner / Main Responsible | Start Date | End Date | Quarter | Partners / Supporters | Cross-Department Collaboration | Estimated Budget | Notes
Sustainable Growth | Choose Internal Audit Committee | Internal Audit | Plan reachout |  | Not Started | High | Olga |  | 2026-02-28 | Q1
Sustainable Growth | Choose Internal Audit Committee | Internal Audit | Reachout to potential candidates |  |  |  | Olga
Sustainable Growth | Choose Internal Audit Committee | Internal Audit | Select candidates | 3-5 candidates |  |  | Olga
Sustainable Growth | Choose Internal Audit Committee | Internal Audit | Present to Board of Directors |  | Not Started | High | Olga |  | 2026-03-05 | Q1
Sustainable Growth | Completion of Volunteers Report | Volunteers Report | Responding to the internal auditor’s questions. |  | Not Started | Medium | Olga |  | 2026-04-15 | Q2 | Full Year
Sustainable Growth | Completion of Volunteers Report | Volunteers Report | Receiving draft report, holding a management meeting to discuss findings, and submitting structured comments. |  | Not Started | Medium | Olga |  | 2026-04-30 | Q2
Sustainable Growth | Completion of Volunteers Report | Volunteers Report | Receiving final report. |  | Not Started | Medium | Olga |  | 2026-05-15 | Q2
Sustainable Growth | Completion of Volunteers Report | Volunteers Report | Board discussion and approval of the report. |  | Not Started | Medium | Olga |  | 2026-06-15 | Q2
Sustainable Growth | Completion of Volunteers Report | Volunteers Report | Building a findings tracking table (finding, risk level, responsible party, deadline). |  | Not Started | Medium | Olga |  | 2026-06-15 | Q2
Sustainable Growth | Completion of Volunteers Report | Volunteers Report | Ongoing monitoring of implementation until findings are closed |  | Not Started | Medium | Olga |  | 2026-12-31 | Q2
Sustainable Growth | Initiation of Additional Report – Corporate Governance | Additional Report | Receiving list of documents required to begin the audit. |  | Not Started | Medium | Olga |  | 2026-10-01 | Q4
Sustainable Growth | Initiation of Additional Report – Corporate Governance | Additional Report | Sending materials to the internal auditor within two weeks. |  | Not Started | Medium | Olga |  | 2026-10-15 | Q4
Sustainable Growth | Initiation of Additional Report – Corporate Governance | Additional Report | Receiving draft report, holding a management meeting to discuss findings, and submitting structured comments. |  | Not Started | Medium | Olga |  | 2026-10-31 | Q4
Sustainable Growth | Initiation of Additional Report – Corporate Governance | Additional Report | Receiving final report. |  | Not Started | Medium | Olga |  | 2026-11-15 | Q4
Sustainable Growth | Initiation of Additional Report – Corporate Governance | Additional Report | Board discussion and approval of the report. |  | Not Started | Medium | Olga |  | 2026-11-30 | Q4
Sustainable Growth | Initiation of Additional Report – Corporate Governance | Additional Report | Building a findings tracking table (finding, risk level, responsible party, deadline). |  | Not Started | Medium | Olga |  | 2026-11-30 | Q4
Sustainable Growth | Initiation of Additional Report – Corporate Governance | Additional Report | Ongoing monitoring of implementation until findings are closed |  | Not Started | Medium | Olga |  | 2026-12-31 | Q4
Financial Independence | Review of Payroll Preparation Process | Payroll Process | Map Existing process |  | Not Started | High | Olga |  | 2026-02-28 | Q1
Financial Independence | Review of Payroll Preparation Process | Payroll Process | Write a draft (include preparation, review, and approval) |  | Not Started | High | Olga |  | 2026-03-20 | Q1
Financial Independence | Review of Payroll Preparation Process | Payroll Process | test |  | Not Started | High | Olga |  | 2026-03-20 | Q1
Financial Independence | Transition to Attendance Reporting in MYHR System | MyHR | Pilot |  | In Progress | High | Olga |  | 2026-04-20 | Q1
Financial Independence | Transition to Attendance Reporting in MYHR System | MyHR | Implement for HQ Employees |  | Not Started | High | Olga |  | 2026-05-01 | Q2
Financial Independence | Transition to Attendance Reporting in MYHR System | MyHR | Plan for teachers |  | Not Started | High | Olga |  | 2026-04-25 | Q2 |  | HR
Financial Independence | Transition to Attendance Reporting in MYHR System | MyHR | Implement for Teachers |  | Not Started | High | Olga |  | 2026-08-15 | Q2 |  | Pedagogy
Financial Independence | Automatic Pension Enrollment | Pensions | Mapping |  | Not Started | Medium | Olga |  | 2026-04-15 | Q2 |  | HR
Financial Independence | Automatic Pension Enrollment | Pensions | Reviewing existing capabilities with the software provider. |  | Not Started | Medium | Olga |  | 2026-04-15 | Q2 |  | HR
Financial Independence | Automatic Pension Enrollment | Pensions | Building tailored onboarding processes for different employee types. |  | Not Started | Medium | Olga |  | 2026-04-30 | Q2 |  | HR
Financial Independence | Automatic Pension Enrollment | Pensions | Drafting an internal procedure for onboarding new employees according to their applicable pension arrangement. |  | Not Started | Medium | Olga |  | 2026-05-31 | Q2 |  | HR
Financial Independence | Automatic Pension Enrollment | Pensions | Producing a monthly report on employees for whom a pension arrangement has not yet been opened |  | Not Started | Medium | Olga |  | 2026-06-30 | Q2
Financial Independence | Develop Internal Financial Information System | Internal Financial System | Defining needs: profit centers, cash flow reports, bank reconciliations. |  | Not Started | High | Olga |  | 2026-07-10 | Q3
Financial Independence | Develop Internal Financial Information System | Internal Financial System | Demonstration meetings with at least three vendors. |  | Not Started | High | Olga |  | 2026-07-20 | Q3
Financial Independence | Develop Internal Financial Information System | Internal Financial System | Receiving price quotes and conducting cost comparison. |  | Not Started | High | Olga |  | 2026-07-30 | Q3
Financial Independence | Develop Internal Financial Information System | Internal Financial System | Selecting a system and obtaining management approval. |  | Not Started | High | Olga |  | 2026-08-15 | Q3
Financial Independence | Develop Internal Financial Information System | Internal Financial System | Building a transition process to the internal system |  | Not Started | High | Olga |  | 2026-09-15 | Q4
Financial Independence | Transition to Monthly Budget and Cash Flow Monitoring | Monthly Budget | Transfer materials to accounting by the 15th of the following month, including credit cards and petty cash. | 1 / month | Not Started | High | Olga |  | 2026-07-15 | Q3
Financial Independence | Transition to Monthly Budget and Cash Flow Monitoring | Monthly Budget | Review monthly accounting records | 1 / month | Not Started | High | Olga |  | 2026-07-30 | Q3
Financial Independence | Transition to Monthly Budget and Cash Flow Monitoring | Monthly Budget | Review monthly budget compliance | 1 / month | Not Started | High | Olga |  | 2026-08-31 | Q3
Financial Independence | Manage the Organization's Annual Budget | Annual Budget | Update budget and cash flow forecast through year-end. |  | Not Started | High | Olga |  | 2026-09-30 | Q3
Financial Independence | Build a Profit Center and Cost Allocation Model | Profit Center and Cost Allocation Model | Mapping |  | Not Started | High | Olga |  | 2026-10-10 | Q4
Financial Independence | Build a Profit Center and Cost Allocation Model | Profit Center and Cost Allocation Model | Implement |  | Not Started | High | Olga |  | 2026-10-31 | Q4
Impact Measurement | Measure Profitability of Organizational Programs | Organizational Profitability | Defining key metrics: number of students per project, project cost, cost per student, program activity hours, cost per teaching hour or per student. |  | Not Started | High | Olga |  | 2026-10-15 | Q4 | Pedagogy | Pedagogy
Impact Measurement | Measure Profitability of Organizational Programs | Organizational Profitability | Building a calculation model. |  | Not Started | High | Olga |  | 2026-10-15 | Q4 | Pedagogy | Pedagogy
Impact Measurement | Measure Profitability of Organizational Programs | Organizational Profitability | Collecting data from various departments within the organization. |  | Not Started | High | Olga |  | 2026-10-31 | Q4
Impact Measurement | Measure Profitability of Organizational Programs | Organizational Profitability | Preparing a report for presentation to the Board of Directors. |  | Not Started | High | Olga |  | 2026-11-15 | Q4
לוודא גבייה מתכנית השנתית - לפרק את המשימה לפי כל רשות (כל רשות מתנהלת שונה)
לוודא גבייה מתכנית הקיץ

## HR
TALMA Strategic Objective | Department Objective | Focus Area | Task Name | KPI | Status | Priority | Primary Owner / Main Responsible | Start Date | End Date | Quarter | Partners / Supporters | Cross-Department Collaboration | Estimated Budget | Notes
Sustainable Growth | Recruitment | Recruitment | Recruit marketing manager | 1 job closed | Planned | Critical | Maayan |  | 15.4.2026 | Q2 |  | Management
Sustainable Growth | Recruitment | Recruitment | Recruit grant manager | 1 job closed | Planned | Critical | Maayan |  | 15.4.2026 | Q3 |  | Management
Sustainable Growth | Recruitment | Recruitment | Design and document the recruitment process - technical and human |  | Planned | Critical | Maayan |  | 28.2.2026 | Q1 | Ido Dvir, Ido M. | Tech | 20000 | Own the full recruitment lifecycle including role definition with hiring managers, job publishing, CV screening, HR interviews, offer coordination, and candidate management through contract signing.
Sustainable Growth | Recruitment | Recruitment System | Design and provide feedback on building of recruitment system
Impact Measurement | HR Measurement & Evaluation | MyHR | Implement my HR - plan |  | In Progress | High | Maayan |  | 31.3.2026 | Q1 |  | Finances | 13000 | Lead the transition to a digital HR management system, including system selection and development based on organizational needs, data preparation and migration, and infrastructure readiness. Implement the system through a structured rollout, including process alignment, training for HR and managers, and ongoing support to ensure effective and consistent use.
Impact Measurement | HR Measurement & Evaluation | MyHR | Implement my HR - deliver for HQ | All HQ employees using my HR | In Progress | High | Maayan |  | 31.3.2026 | Q1 |  | Finances |  | Lead the transition to a digital HR management system, including system selection and development based on organizational needs, data preparation and migration, and infrastructure readiness. Implement the system through a structured rollout, including process alignment, training for HR and managers, and ongoing support to ensure effective and consistent use.
Impact Measurement | HR Measurement & Evaluation | MyHR | Implement my HR - deliver for teachers | All teachers using MyHR | In Progress | High | Maayan |  | 31.3.2026 | Q1 |  | Finances |  | Lead the transition to a digital HR management system, including system selection and development based on organizational needs, data preparation and migration, and infrastructure readiness. Implement the system through a structured rollout, including process alignment, training for HR and managers, and ongoing support to ensure effective and consistent use.
Sustainable Growth | Onboarding | Onboarding | Structured Onboarding program - plan |  | Planned | Critical | Maayan |  | 28.2.2026 | Q1 |  | Finances | - | Lead the onboarding process including employment contracts, document collection, first-day coordination, stakeholder introductions, and structured onboarding meetings.
Sustainable Growth | Onboarding | Onboarding | Structured Onboarding program - deliver
National Recognition | Culture & Welfare | TALMA HQ events | Build organizational event/holiday schedule |  | Planned | Medium | Maayan |  | 31.3.2026 | Q3 |  | Finances | 100000 | Plan and execute holidays, team events, onboarding celebrations, farewells, and initiatives that foster belonging and engagement.
Financial Independence | Compliance | Compliance | Sexual harassment prevention - create policy document |  | In Progress | High | Maayan |  | 28.2.2026 | Q2 |  | Full Year | 5000 | Full responsibility for serving as the Sexual Harassment Prevention Officer, including building and maintaining a structured organizational process: policy review and updates, clear reporting and handling procedures, documentation, manager briefings, employee awareness, and compliance with legal requirements.
Financial Independence | Compliance | Compliance | Sexual harassment prevention - deliver |  | In Progress | High | Maayan |  | 28.2.2026 | Q2 |  | Full Year | 5000 | Full responsibility for serving as the Sexual Harassment Prevention Officer, including building and maintaining a structured organizational process: policy review and updates, clear reporting and handling procedures, documentation, manager briefings, employee awareness, and compliance with legal requirements.
Sustainable Growth | Offboarding | Offboarding | Structured Offboarding program - plan |  | Planned | Critical | Maayan |  | 28.2.2026 | Q1 |  | Finances | - | Manage exit conversations, termination documentation, rights calculation in coordination with finance, and respectful knowledge transfer.
Sustainable Growth | Offboarding | Offboarding | Structured off boarding program - deliver |  |  |  | Maayan
Sustainable Growth | Office Operations | Office Renovation | Office Renovation - plan |  | Planned | High | Maayan |  | 31.5.2026 | Q2 |  | Finance, Management | 500000 | Prepare a detailed operational and logistical plan for office renovation and expansion, pending budget approval.
Sustainable Growth | Office Operations | Office Renovation | Office Renovation - deliver |  |  |  | Maayan
Sustainable Growth | Office Operations | Office Maintenance | Optimize office operations and vendor management. |  |  |  | Maayan |  | 31.12.2026 | Q4 |  |  | 50000 | Manage office logistics vendors including cleaning, maintenance, communication services, supplies, and ongoing operational needs.
Impact Measurement | HR Measurement & Evaluation | Formal Employee Feedback | Formal Feedback - Plan | 2 / year | Not Started | Medium | Maayan |  | 31.8.2026 | Q3 |  | Tech | ? | Develop feedback and evaluation processes, support role development, promotions, and performance conversations.
Impact Measurement | HR Measurement & Evaluation | Formal Employee Feedback | Oversee HQ employees feedback | 2 / year | Not Started | Medium | Maayan |  | 31.8.2026 | Q3 |  | Tech | ? | Develop feedback and evaluation processes, support role development, promotions, and performance conversations.
Impact Measurement | HR Measurement & Evaluation | Formal Employee Feedback | Formal Feedback - based on employee needs | 2 / year | Not Started | Medium | Maayan |  | 31.8.2026 | Q3 |  | Finances | ? | Develop feedback and evaluation processes, support role development, promotions, and performance conversations.
National Recognition | Conference Management | Conference / Event Management | Formalize processes for TALMA conferences and events. |  | Not Started | Medium | Maayan |  | 31.7.2026 | Q3 |  | Programs, Finance, Marketing | ? | Develop a structured process for planning and managing conferences and events, including event types, roles and ownership, scope, vendor and production company engagement, and alignment with the approved budget.
Sustainable Growth | Improve Employee Retention | Improve Employee Retention | Employee retention plan - update and provide support | 1 / quarter | Not Started | Low | Maayan |  | 31.10.2026 | Q4 |  | Tech | ? | Support managers with employee retention, conflict handling, and alignment between organizational needs and employee wellbeing.
Financial Independence | Office Operations | Annual Budget, Ministry of Education | Coordinate GEFEN program submissions. |  | Planned | High | Maayan |  | 31.12.2026 | Q1 |  | Finances | - | Serve as the logistical focal point for GEFEN program submissions, ensuring coordination and timely updates across relevant stakeholders.

## Resource - ISR
TALMA Strategic Objective | Department Objective | Focus Area | Task Name | KPI | Status | Priority | Primary Owner / Main Responsible | Start Date | End Date | Quarter | Partners / Supporters | Cross-Department Collaboration | Estimated Budget | Notes
Financial Independence | Optimizing development team operations | Cooperation between Resource Departments | Establish a clear division of responsibilities, project alignment, and ongoing partnership with TALMA USA
Financial Independence | Optimizing development team operations | Cooperation between Resource Departments | Weekly meeting with Resources-USA | 1/week
Financial Independence | Optimizing development team operations | Cooperation between Resource Departments, Grants | Build a grant management system, together with Resources-USA |  | Done | High | Shay |  | 31.3.26 | Q1
Financial Independence | Optimizing development team operations | Recruitment | Recruit addition staff member at 50-100% |  | Planned | High | Shay |  | 2026-04-30 | Q1 | HR |  |  | איפיון התפקיד גיוס לתפקיד חפיפה
Financial Independence | Optimizing development team operations | Improve Professional Skills | Build professional fundraising skills |  | Planned | High | Shay |  | 30.6.26 | Q2 | Resources - USA
Financial Independence | Develop funding sources | Foundations | Connect with new foundations | 7 |  |  | Shay |  | 30/6/26 | Q2
Financial Independence | Develop funding sources | Foundations | Connect with new foundations | 5 |  |  | Shay |  | 31/12/26 | Q4
Financial Independence | Develop funding sources | Summer Program, General Fundraising | Secure budget for Summer Program | NIS 1,000,000 | Not Started | Critical | Shay |  | 30.6.26 | Q2 | Resources - USA |  |  | להוסיף תשלום על הקיץ (אשקלון, אילת, בן שמן) מציאת רשויות חזקות עם יכולות מימון בניית תמהיל של מורי חול מול מורים ישראלים משקיעים לתוכנית קיץ (דגש על פדרציות)
Financial Independence | Develop funding sources | Grants, Summer Program | Apply designated grants to cover summer budget gaps |  |  |  | Shay |  | 31/12/26
Financial Independence | Develop funding sources | Government Relationships | Develop strategic relationships with government ministries | 2 | Planned | High | Shay |  | 30.9.26 | Q3 |  |  |  | עם הקבינט: מורים עולים- משרד העלייה והתפוצות עם הקבינט: מורים עולים- משרד העלייה והתפוצות
Financial Independence | Develop funding sources | Foundations | Securing a major long-term philanthropic partner |  | Not Started | Critical | Shay |  | 30.12.26 | Q4 | Resources - USA |  |  | מול עידו- איפה הדברים מול קקל + שוסטרמן וסטיינהרט- סיוע בפניות ליד הנדיב ולקרן עזריאלי פנייה ליד הנדיב (פוטנציאל ל-1-2 מלש"ח כל שנה) קק"ל: אור קבינט- ליואל קשרים בקקל
Financial Independence | Develop funding sources | Foundations | Securing a Mid-level long-term philanthropic partner |  | Not Started | Critical | Shani |  | 30.12.26 | Q4 | Resources - USA |  |  | פנייה לעתר רזי אורן- מנכלית קרן יחד פנייה למדי יעקובוזון- מנהלת השקעות של משפחת קרסו (מתבסס על חברת פריסבי לשעבר קרסו מוטורוס) פנייה לקרן אדליס (הכוונה של עומר יעדים)
Financial Independence | Develop funding sources | Business Partnerships | Build business partnerships - plan |  | Not Started | High | Shani |  | 30.9.26 | Q3 |  |  |  | Build a designated program for partnerships with businesses. מיפוי עסקים לשותפות פוטנציאלית / אחריות תאגידית ¦ Develop TALMA program for High-Tech פגישת קפה עם בעלי תפקיד מקביל בארגונים אחרים פנייה לציונות 2000 - קשרי מעסיקים Schedule 4 meetings with potential business partners by the end of Q3 Schedule additional 4 meetings with potential business partners by the end of Q3
Financial Independence | Develop funding sources | Business Partnerships | Build business partnerships - schedule meetings | 8 | Not Started | High | Shani |  | 30.9.26 | Q3 |  |  |  | לקבוע פגישות + פגישה עם חברת כוח אדם - לקבל נתונים
Financial Independence | Develop funding sources | Business Partnerships | Build business partnerships - meetings status check | 1 / 2 months | Not Started | High | Shani |  | 30.9.26 | Q3
Financial Independence | Develop funding sources | Business Partnerships | Build business partnerships - deliver |  | Not Started | High | Shani |  | 30.9.26 | Q3
Financial Independence | Strengthen existing funders | Foundations | Update donor record with program progress, achievements and special events (including invitation to main events) | 1 / quarter | In Progress | Medium | Shay |  | 30.6.26 | Q2
Financial Independence | Strengthen existing funders | Foundations, Newsletters | Send donors newsletter | 1 / quarter
Financial Independence | Strengthen existing funders | Foundations, Newsletters | Holiday greetings | 2 / year
Financial Independence | Strengthen existing funders | Foundations | Send birthday greetings | 1/ / month
Financial Independence | Develop funding sources | Organizational Partnerships | Build organizational partnerships - plan |  |  |  | Shani |  | 31.7.26
Financial Independence | Develop funding sources | Organizational Partnerships | Build organizational partnerships - schedule meetings
Financial Independence | Develop funding sources | Organizational Partnerships | Build organizational partnerships - deliver
National Recognition | Develop income generating initiatives | TALMA Academy | Plan |  | In Progress | Medium | Shani |  | 30.3.26 | Q1 | Pedagogy |  |  | מציאת מקום (בית ברל / ירושלים) חידוד המוצר והמודל
Financial Independence | Develop income generating initiatives | TALMA Academy, General Fundraising | Find Funding
National Recognition | Develop income generating initiatives | TALMA Academy | Build program and partnerships for Arab Community Program | [10 empty] | תוכנית ייעודית להכשרת מורים ערבים + שתפ עם קרן ביידר + החברה למתנסים
National Recognition | Develop income generating initiatives | TALMA Academy | Build program and partnerships for Haredi Community Program | [10 empty] | תוכנית ייעודית למורים חרדים- דרך בית שמש או ירושלים ושת"פ עם הממ"חים
Financial Independence | Optimizing development team operations | Annual Budget | Establishing pricing model for TALMA's products |  | In Progress | High | Shay |  | 30.9.26 | Q3 | Finances
Financial Independence | Optimizing development team operations | Recruitment System, Recruitment | Establishing nation wide teacher data base |  | In Progress | High | Shay |  | 30.6.26 | Q2 | Pedagogy, HR, Tech |  |  | חידוד מוגל גיוס מורים + קמפיין בניית תהליך מנוהל בתוך תלמא (בשיתוף מעיין דניאל אטל וסיון)
Financial Independence | Develop income generating initiatives | Develop new municipalties | Build models for existing programs | 3 | In Progress | High | Shani |  | 30.6.26 | Q2 | Pedagogy |  |  | בני עיש, נס ציונה, מרחבים
Financial Independence | Strengthen existing municipalties | Develop new municipalties | Map existing TALMA programs |  | In Progress | High | Shay |  | 30.6.26 | Q2 | Pedagogy, HR, Tech |  |  | מיפוי תכנית קיימות בתלמ״א
Financial Independence | Strengthen existing municipalties | Develop new municipalties | Map municiplalities (with an eye on program expansion) | [10 empty] | רשויות רלוונטיות לתכניות תלמא - מהעבר או מעכשיו. מי יכול מעוניין בתכנית שלנו? זה עוזר להבין הייתכנות להרחבת של אחריי וזיקים,
Financial Independence | Develop income generating initiatives | Develop new municipalties | Close deal with municipality on program expansion | 2? | In Progress | High | Shani |  | 30.6.26 | Q2 | Pedagogy |  |  | בני עיש, מס ציונה מרחבים
Financial Independence | Develop income generating initiatives |  | Developing pre school programs |  | In Progress | High | Shay |  | 30.9.26 | Q3 | Pedagogy
National Recognition | Increasing potential financial partners exposure to TALMA | TALMAisrael.com website, Website Advertising | Developing Hebrew TALMA's web site |  |  |  | Shay |  | 30.6.26 | Q2 | Tech
Sustainable Growth | Strengthen existing municipalties | Full Year, Evaluation - Internal | Principals survey - receive |  |  |  | Miri
Sustainable Growth | Strengthen existing municipalties | Full Year | Mid-year meetings with municipalities | ?? |  |  | Shay |  | 15.2 |  | Full Year, Pedagogy |  |  | לאחר תוצאות סקר מנהלים + המשך שיח על שנה הבאה
Sustainable Growth | Strengthen existing municipalties | Full Year | Close contracts with municipalities for next year | ?? |  |  | Shay |  | 1.5 |  | Finances
Sustainable Growth | Strengthen existing municipalties | Full Year, Evaluation - Reporting to External people | End of year evaluations - request |  |  |  | Shay |  |  |  | Pedagogy
Sustainable Growth | Strengthen existing municipalties | Full Year, Evaluation - Reporting to External people | End of year evaluations - receive |  |  |  | Shay |  |  |  | Pedagogy
Sustainable Growth | Strengthen existing municipalties | Full Year | End-of-year meetings with municipalities | ?? |  |  | Shay |  | 1.6 |  | Pedagogy, Full Year
Sustainable Growth | Strengthen existing municipalties | Summer Program | Initial conversations with municipalities about next summer | ?? |  |  | Shay |  | 1.1
Sustainable Growth | Strengthen existing municipalties | Summer Program | Followup conversations with municipalities about next summer | ?? |  |  | Shay |  | 1.1
Sustainable Growth | Strengthen existing municipalties | Summer Program | Closing deal conversations with municipalities about next summer | ?? |  |  | Shay |  | 1.4
Sustainable Growth | Strengthen existing municipalties | Summer Program | End of year conversations with municipalities |  |  |  | Shay |  | 15.8 |  | Pedagogy
Sustainable Growth | Strengthen existing municipalties | Summer Program, Evaluation - Reporting to External people | End of year evaluations - request
Sustainable Growth | Strengthen existing municipalties | Summer Program, Evaluation - Reporting to External people | End of year evaluations - receive
Sustainable Growth | Strengthen existing municipalties | Evaluation - Internal, Bnei Ayish | Principals survey - receive | [5 empty] | 15.2
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Bnei Ayish | Mid-year meetings with municipalities | [5 empty] | 15.2 |  |  |  |  | Includes conversation about next year
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Bnei Ayish | Close contract for next year | [5 empty] | 1.5
Sustainable Growth | Strengthen existing municipalties | Evaluation - Reporting to External people, Bnei Ayish | Evaluations - request
Sustainable Growth | Strengthen existing municipalties | Evaluation - Reporting to External people, Bnei Ayish | Evaluations - recieve
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Bnei Ayish | End-of-year meetings with municipalities | [5 empty] | 1.6
Sustainable Growth | Strengthen existing municipalties | Evaluation - Internal, Merhavim | Principals survey - receive
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Merhavim | Mid-year meetings with municipalities
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Merhavim | Close contract for next year
Sustainable Growth | Strengthen existing municipalties | Evaluation - Reporting to External people, Merhavim | Evaluations - request
Sustainable Growth | Strengthen existing municipalties | Evaluation - Reporting to External people, Merhavim | Evaluations - recieve
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Merhavim | End-of-year meetings with municipalities
Sustainable Growth | Strengthen existing municipalties | Evaluation - Internal, Ness Ziona | Principals survey - receive
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Ness Ziona | Mid-year meetings with municipalities
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Ness Ziona | Close contract for next year
Sustainable Growth | Strengthen existing municipalties | Evaluation - Reporting to External people, Ness Ziona | Evaluations - request
Sustainable Growth | Strengthen existing municipalties | Evaluation - Reporting to External people, Ness Ziona | Evaluations - recieve
Sustainable Growth | Strengthen existing municipalties | Strengthen existing municipalties, Ness Ziona | End-of-year meetings with municipalities
Financial Independence | Develop funding sources | Grants | Submit 100% relevant grants - plan | [10 empty] | עדכון טבלה במאנדיי (grant management), סנכרון של כל בעלי התפקידים הרלוונטיים על הטבלה. חלוקת אחריות על גרנטים בין אנשי הצוות. תיקיית טמפלטים לבקשות מענק (אודות תלמ״א, אודות קיץ/שנתית וכו׳)...
Financial Independence | Develop funding sources | Grants | Submit 100% relevant grants - followup | 1/ month ??
Financial Independence | Develop income generating initiatives | Develop new municipalties, Educator Communities | Promote Israeli educator communities - plan |  | Planned | Low | Shani |  | 30.9.26 | Q3 | HR, Pedagogy |  |  | לבנות מיני תכנית עבודה למשימת קהילות מחנכים מיפוי אגונים פוטנציאליים לשת״פ בניית טמפלייט בסיס לפניייה לשותפים (על בסיס הפנייה לתוצרת הארץ) שיתוף פעולה עם רשויות בהיבט של גיוס ודיוק הטבות למועמדים (מגורים, מענק שנתי...)
Financial Independence | Develop income generating initiatives | Bnot Sherut, Develop new municipalties | Study Bnot Sherut Program and Recruitment
Financial Independence | Develop income generating initiatives | Bnot Sherut, Strengthen existing municipalties | Schedule meeting Bat Ami
Financial Independence | Develop income generating initiatives | Organizational Partnerships | Connect with school networks (Darka, Ort...)
National Recognition | Increasing potential financial partners exposure to TALMA | TALMA Events - Annual Conference | Study previous events and draw conclusions
National Recognition | Increasing potential financial partners exposure to TALMA | TALMA Events - Annual Conference | Present idea for next year's conference
National Recognition | Increasing potential financial partners exposure to TALMA | TALMA Events - Annual Conference | Recruit funding sources for next year's conference
|  | TALMA Events - Ministry of Science | [11 empty] | אם הדבר הזה יקרה, צריך לשים משימות
TALMA Events - Annual Conference

## Tech
TALMA Strategic Objective | Department Objective | Focus Area | Task Name | KPI | Status | Priority | Primary Owner / Main Responsible | Start Date | End Date | Quarter | Partners / Supporters | Cross-Department Collaboration | Estimated Budget | Notes
Impact Measurement | Evaluation and Measurement | Bnei Ayish, TALMA.digital | Bnei Ayish Assessment |  | Done | Critical | Daniel |  | 2025-12-15 | Q1 | Stacey | Pedagogy
Sustainable Growth | Improve Internal Tools | DAM tool Implementation | DAM tool |  | Not Started | Low | Daniel |  |  | Q4 |  | Marketing
Sustainable Growth | Improve Data Security | Compliance | Data / Information Security - DPO Course |  | Done | High | Daniel |  |  | Q1
Sustainable Growth | Improve Data Security | Compliance | Data / Information Security - Ensure safe data practices for fellowship applicants |  | Planned | High | Daniel |  |  | Q2 | T'helah | Resources - USA
Sustainable Growth | Improve Data Security | Compliance | Data / Information Security - Minimize existing sensitive data |  | In Progress | High | Daniel |  |  | Q1, Q2 | T'helah, Miri | Resources - USA, Full Year
Sustainable Growth | Improve Data Security | Compliance | Data / Information Security - 2FA enforcement for Google Workspace |  | Done | Critical | Daniel |  |  | Q1
Sustainable Growth | Improve Data Security | Compliance | Data / Information Security - Cybersecurity policy - create |  | Blocked | Critical | Daniel |  | 2026-05-14 | Q3
Sustainable Growth | Improve Data Security | Compliance | Data / Information Security - Cybersecurity policy - implement |  | On Hold | High | Daniel |  | 2026-07-01 | Q3
Sustainable Growth | Map existing hardware providers | Compliance | Data / Information Security - Map existing hardware providers |  | Done | Critical | Daniel |  |  | Q1
Sustainable Growth | Map existing software systems | Compliance | Data / Information Security - Map existing software systems |  | Done | High | Daniel |  |  | Q1
Sustainable Growth | Improve Internal Tools | TALMA Curriculum App | Pedagogy Lesson Plan Creation / "Bookshelf" App |  | Planned | High | Daniel |  |  | Q3 | Etelle | Pedagogy
Sustainable Growth | Improve Internal Tools | Google Drive | Google Drive Reboot - Planning |  | Planned | High | Daniel |  |  | Q3
Sustainable Growth | Improve Internal Tools | Google Drive | Google Drive Reboot - Implementation |  |  |  | Daniel |  |  | Q4
Sustainable Growth | Improve Internal Tools | Monday.com Implementation | monday.com Reboot |  | In Progress | High | Daniel |  |  | Q1 | Sagi, Ido Dvir
Sustainable Growth | Improve Internal Tools | Monday.com Implementation | monday.com Reboot |  | In Progress | High | Daniel |  | 2026-04-09 | Q2 | Sagi, Ido Dvir
Sustainable Growth | Improve Client Facing Tools | Practice Pal | Practice Pal - finish WeSpeak |  | In Progress | Medium | Daniel |  |  | Q1 | Leila, Jennifer | Pedagogy
Sustainable Growth | Improve Client Facing Tools | Practice Pal | Practice Pal - voice recognition |  |  |  | Daniel |  |  | Q4
National Recognition | Improve Client Facing Tools | Recruitment System | Newsletter - Tech Support |  | In Progress | Medium | Daniel |  |  | Q2 | Adi | Resources - Israel, Resources - USA
Sustainable Growth | Improve Internal Tools | Recruitment System | Build Recruitment System |  | Not Started | Critical | Daniel |  |  | Q2 | Maayan, Ido Dvir | HR
Sustainable Growth | Improve Internal Tools | Slack Implementation | Adopt Slack |  | Done | Critical | Daniel |  | 2025-12-15 | Q1
National Recognition | Improve Client Facing Tools | TALMA.digital | TALMA.digital - Online Lessons |  | Blocked | Medium | Daniel |  |  | Q1, Q2
National Recognition | Improve Internal Tools | TALMA.digital | TALMA.digital - All teachers and programs included in system
National Recognition | Improve Internal Tools | TALMA.digital | TALMA.digital - Ministry of Education authorization |  | In Progress | High | Daniel |  |  | Q2 |  | Pedagogy
International Presence | Improve Client Facing Tools | TALMAisrael.com website | TALMAisrael.com - Hebrew site |  | In Progress | High | Daniel |  | 2026-01-18 | Q2 | Shay, Shani | Pedagogy, Resources - Israel
International Presence | Improve Client Facing Tools | TALMAisrael.com website | TALMAisrael.com - Design |  | In Progress | High | Daniel |  | 2026-01-18 | Q1 | Shay, Shani | Pedagogy, Resources - Israel
International Presence | Improve Client Facing Tools | TALMAisrael.com website | TALMAisrael.com - Blog | [6 empty] | Q1, Q2